## Nov 24
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Review backend API | Update News/News Details with fetch API
Thanh | Update Login, Register, book appointment, ApointmentList with fetch API | Update Login, Register with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang

## Nov 25
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update News/News Details with fetch API | Update Services with fetch API
Thanh | Update Login, Register with fetch API | Update Login, Register with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang

## Nov 26
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Services with fetch API | Update Admin Dashboard: User List
Thanh | Update Login, Register with fetch API | Update Login, Register, appointmentList with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang

## Nov 27
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Admin Dashboard: Users Management | Update Admin Dashboard: Services Management
Thanh | Update Login, Register, appointmentList with fetch API | Update Login, Register, appointmentList with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang

## Nov 28
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Admin Dashboard: Services Management | Update Admin Dashboard: Contents Management
Thanh | Update Login, Register, appointmentList with fetch API | Update Login, Register, appointmentList, Bookappointment with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang

## Dec 1
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Admin Dashboard: Contents Management | Update Admin Dashboard: Banners Management
Thanh | Update Login, Register, appointmentList, Bookappointment with fetch API | Update Login, Register, appointmentList, Bookappointment with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang |  | Update FAQ in Contact page with fetch API

## Dec 2
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Admin Dashboard: Banners Management | Update Admin Dashboard: Admin Profile
Thanh | Update Login, Register, appointmentList, Bookappointment with fetch API | Update Login, Register, appointmentList, Bookappointment with fetch API
Nhut | Authorisation for API | Authorisation for API
Hoang | Update FAQ in Contact page with fetch API | Update FAQ in Contact page with fetch API

## Dec 3
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Admin Dashboard: Admin Profile | Update Doctor Dashboard: Avaiability
Thanh | Update Login, Register, appointmentList, Bookappointment with fetch API | Update Login, Register, appointmentList, Bookappointment with fetch API
Nhut | Implement AI | Implement AI
Hoang | Update FAQ in Contact page with fetch API | Write test for Backend services

## Dec 4
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Doctor Dashboard: Availability | Update Appointment Flow: fetch Service, Doctor, Time API
Thanh | Update Login, Register, appointmentList, Bookappointment with fetch API | Update Login, Register, appointmentList, Bookappointment with fetch API
Fix responsive
Nhut | Simplify database | Simplify database
Hoang | Write test for Backend services | Write test for Backend services

## Dec 8
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update Appointment Flow: fetch Service, Doctor, Time API | Test Appointment Flow: fetch Service, Doctor, Time API
Thanh | Update Login, Register, appointmentList, Bookappointment with fetch API | Update Admin Dashboard: FAQs Management
Fix responsive
Nhut | Chatbox FE | Chatbox FE
Hoang | Write test for Backend services | Write test for Backend services

## Dec 9
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Test Appointment Flow: fetch Service, Doctor, Time API | Presentation prep
Thanh | Update Admin Dashboard: FAQs Management | Presentation prep
Nhut | Presentation prep | Presentation prep
Hoang | Write test for Backend services | Presentation prep