## Oct 27
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Reviewed Trello | Start learning Figma | N/A
Setuped project environment
Thanh | Drawed draft UI | Continue learning Figma | N/A
Learned Figma
Nhut | Build up ideas for Website | Figure out User stories (Doctors, Admin) | N/A
Determined User Stories (User)
Hoang | Learnt HTML & CSS | Work with Nhut to determine US

## Oct 28
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Learnt Figma | Continue learning Figma | N/A
Thanh | Learnt Figma | Continue learning Figma | N/A
Nhut | Determined User Stories (Doctor) | Continue with US | N/A
Updated Product Backlog
Hoang | Worked with Nhut to determine US | Work with Nhut to determine US | N/A

## Oct 29
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Learnt Figma | Continue learning Figma | N/A
Thanh | Learnt Figma | Start Figma design | N/A
Nhut | Determined User Stories (Admin) | Update product backlog | N/A
Hoang | Worked with Nhut to determine US | Update product backlog | N/A

## Oct 30
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Learnt Figma | Start design prototype (Homepage) | N/A
Thanh | Started design prototype (About Us) | Continue design prototype (Services) | N/A
Nhut | Updated US and PB for Admin | Continue US
Hoang | Updated US and PB for Doctor | Learn Figma | N/A

## Oct 31
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Worked on prototype (Homepage) | Continue doing prototype (Doctor Dashboard) | N/A
Thanh | Worked on prototype (Services, Service Details) | Continue doing prototype (News) | N/A
Nhut | Updated US for User | Learn Figma | N/A
Hoang | Learnt Figma | Continue learning Figma | N/A

## Nov 3
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Worked on prototype (Doctor Dashboard) | Continue doing prototype (Admin Dashboard) | N/A
Thanh | Worked on prototype (News, News Detail) | Continue doing prototype (Appointment) | N/A
Nhut | Learnt Figma | Start working on prototype (Login, Register) | N/A
Hoang | Learnt Figma | Start working on prototype (Contact Us) | N/A

## Nov 4
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Worked on prototype (Admin Dashboard) | Make draft version of presentation | N/A
Thanh | Worked on prototype (Appointments) | Continue doing prototype (User Dashboard - Main) | N/A
Nhut | Worked on prototype (Login, Register) | Continue doing prototype (User Dashboard - Appointments) | N/A
Hoang | Worked on prototype (Contact Us) | Continue doing prototype (User Dashboard - Prescriptions) | N/A

## Nov 5
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Draft version of presentation | Update content for presentation: Sprint Ceremonies & Insights, Team Contributions | N/A
Thanh | Worked on prototype (User Dashboard - Main) | Update content for presentation: Prototype | N/A
Nhut | Worked on prototype (User Dashboard - Appointments) | Update content for presentation: User Stories & Backlog | N/A
Hoang | Worked on prototype (User Dashboard - Prescriptions) | Update content for presentation: Project Overview | N/A

## Nov 6
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Update content for presentation: Sprint Ceremonies & Insights, Team Contributions | Presentation check | N/A
Thanh | Update content for presentation: Prototype | Presentation check | N/A
Nhut | Update content for presentation: User Stories & Backlog | Presentation check | N/A
Hoang | Update content for presentation: Project Overview | Presentation check | N/A