## Nov 10
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Presentation sprint 1 | FE tasks (convert Figma to HTML)
Setup project environments (Frontend, Backend)
Thanh | Presentation sprint 1 | divide task: start frontend(convert figma to HTML)
Discuss front end, back end
Nhut | Presentation sprint 1 | BE tables
Planning BE Databases
Hoang | Presentation sprint 1 | BE tables
Discuss front end, back end

## Nov 11
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Footer, Bottom Bar) | Convert Figma to components (Hero)
Thanh | Convert Figma to components (Topbar, Header) | Convert Figma to components (HomePage)
Nhut | Building databases | Building databases
Hoang | Building databases | Building databases

## Nov 12
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Hero) | Create common Layout, and Route
Thanh | Convert Figma to components (Homepage) | Convert Figma to components (Services)
Nhut | Building databases | Building databases
Hoang | Building databases | Building databases

## Nov 13
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Create common Layout, and Route | Convert Figma to components (News)
Thanh | Convert Figma to components (Services) | Convert Figma to components (Service Details)
Nhut | Building databases with MongoDB | Building databases with MongoDB
Hoang | Building databases with MongoDB | Building databases with MongoDB

## Nov 14
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (News Details) | Convert Figma to components (Login, Register)
Thanh | Convert Figma to components (Service Details) | Convert Figma to components (Contact Us)
Nhut | Building databases with MongoDB | Building databases with MongoDB
Hoang | Building databases with MongoDB | Building databases with MongoDB

## Nov 17
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Login, Register) | Convert Figma to components (Dashboard)
Thanh | Convert Figma to components (Contact Us) | Convert Figma to components (Appointment, Confirm, Calendar)
Nhut | Building databases with MongoDB | Checking working database & working on LLM for project
Hoang | Building databases with MongoDB | Prepare presentation

## Nov 18
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Dashboard) | Convert Figma to components (Admin Dashboard: Appointments, Services)
Convert Figma to components (Admin Dashboard: Users)
Thanh | Convert Figma to components (Appointment, Confirm, Calendar) | Convert Figma to components (User Dashboard: userProfile,AppointmentCard, PrescriptionCard,Prescriptions,)
Nhut | Implement LLM to project | Implement LLM to project
Hoang | Prepare Presentation | Prepare Presentation

## Nov 19
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Admin Dashboard: Appointments, Services) | Convert Figma to components (Admin Dashboard: Content, Banners, Profile)
Thanh | Convert Figma to components (User Dashboard: userProfile,AppointmentCard, PrescriptionCard,Prescriptions,) | Convert Figma to components (Dotor Dashboard: doctorProfile, doctorDbCard, AppointmentList, PatientCard, PatientList)
Nhut | Review Database | Pre-Presentation Sprint 2
Hoang | Prepare presentation | Convert Figma to components DoctorProfile and DoctorProfileForm

## Nov 20
Attendance
Ngoc, Thanh, Nhut, Hoang
TEAM REPORT
Member | Yesterday’s progress | Today plan | Blockers
Ngoc | Convert Figma to components (Admin Dashboard: Content, Banners, Profile) | Project review
Prepare Presentation
Thanh | Convert Figma to components (Dotor Dashboard: doctorProfile, doctorDbCard, AppointmentList, PatientCard, PatientList) | Convert Figma to components (Dotor Dashboard: doctorProfile, doctorDbCard, AppointmentList, PatientCard, PatientList)
Nhut | Project Review | Prepare Presentation
Hoang | Convert Figma to components DoctorProfile and DoctorProfileForm | Prepare Presentation